## Sheet1
LMIS PROJECT TIMELINE
TASKS | DESCRIPTION | NO. OF DAYS (Holidays and weekend not included) | TARGET START | TARGET END | PERCENT DONE | PERSON RESPONSIBLE
Data Gathering |  | DONE
UI Template |  | DONE
Database Design |  | DONE
Dashboard |  | DONE
Adjudication Committee |  | DONE
Signatories | with barcode and QR code to be generated per assigned signatory | 5 | 2017-09-11 | 2017-09-15
Nature of cases | CRUD | DONE
| folder colors | 5 | 2017-06-27 | 2017-07-03 | 80% | Ronnel
Directory | sync contacts with registered entities from etransact | 3 | 2017-06-22 | 2017-06-27 | 50% | Jera
Calendars | Agency, Adjudication, Personal | 1 | 2017-06-22 | 2017-06-22 | 80% | Jera
Cases | Design (Pending, For Compliance, Closed) | 3 | 2017-06-21 | 2017-06-23 | 20% | Ronnel
| Create Case | 3 | 2017-06-21 | 2017-06-23 | 80%% | Ronnel
Summons | Email Sending | 15 | 2017-07-04 | 2017-07-24 |  | Jera
| Letter Format | 15 | 2017-07-04 | 2017-07-24 |  | Ronnel
Template |  | 5 | 2017-08-15 | 2017-08-21 |  | Ronnel
Upload Case | Files submitted to be converted as img to integrate with the page flipping feature of cases | 15 | 2017-07-25 | 2017-08-14 |  | Ronnel
Events | Minutes of the Meeting of Case Hearing | 8 | 2017-06-28 | 2017-07-07 |  | Jera
Includes Recording of the session, archive of files submitted, attendees, etc.
Session & UAC | not priority but needed for the personal calendar of the users | 2 | 2017-08-24 | 2017-08-25 | 30% | Jera
Text Messaging | Text message notification for the adjudication committee, aside from the calendar in the system | 15 | 2017-08-29 | 2017-09-11 |  | jera & ronnel
TARGET COMPLETION DATE: AUGUST 26, 2017